Project Brief

Hardware Collection — Digital Transformation & Local Lead-Generation System

Prepared by: Aayush  |  Date: 29 July 2026  |  Version: Retroactive baseline, reflecting work completed to date

# Executive Summary

Hardware Collection is a 20+ year, family-owned architectural hardware showroom in Sakchi, Jamshedpur, and an authorized dealer for Hafele, Dorset, Labacha, Godrej, Hettich, and Kich. Despite a strong local reputation (4.4★, 55+ reviews), the business's digital presence is underdeveloped — it relies on third-party directories (Justdial, IndiaMART), has no owned website, and shares its name with an unrelated Kolkata-based brand, creating a real risk of customer confusion. This project builds a proportionate, Tier-2-appropriate digital system — prioritized as GMB/Local SEO → WhatsApp Business → Website → Social — to convert existing offline trust into local search visibility, WhatsApp inquiries, and showroom visits. The website is a trust and lead-generation tool, not an e-commerce platform.

# Project Goals

- Increase qualified local leads (calls, direction requests, WhatsApp inquiries).

- Establish a disambiguated, Jamshedpur-specific digital identity (domain, GMB, social handles).

- Convert the business's 20-year offline reputation into digital trust signals (reviews, photos, citations).

- Modernize the brand's visual identity while keeping recommendations sized for a single-location Tier-2 retail showroom.

# Success Metrics

| GMB Profile Completeness | 55% → 90%+ |
| --- | --- |
| Google Reviews | 55 → 200+ |
| Map Pack Ranking | Top-3 for "hardware shop Sakchi" |
| Monthly Calls | ~15 → 80+ |
| Monthly Direction Requests | ~30 → 120+ |
| Website | Live, indexed, and generating WhatsApp/call conversions |

# Scope

Included

- Google Business Profile optimization and ongoing local SEO management.

- WhatsApp Business setup with standardized number (919835190738) and pre-filled CTA messages.

- Website design and build (Next.js 14 + Tailwind + Vercel) per the delivered PRD and vibe-coding prompt pack.

- 21-file enterprise knowledge base and Notion-based Task OS for ongoing operations.

- Competitor intelligence and 90-Day Sakchi Map Domination Blueprint.

- Content calendar, response template library, and review-generation system.

Excluded

- E-commerce, online checkout, or payment processing on the website.

- Paid media/ad campaign management (unless separately scoped).

- Vendor pricing negotiations, GST filings, or other financial/legal commitments — these remain Mukesh's decisions.

- Professional photography/videography production (unless separately scoped).

# Target Audience

- Primary: Homeowners and renovators (30–55) investing in long-term property value.

- Secondary: Interior designers, architects, and contractors making procurement decisions for clients.

- Geographic: Jamshedpur and surrounding townships (Adityapur, Sonari, Telco, Kadma).

- Key pain points: durability in a humid/industrial climate, technological complexity of digital locks, decision fatigue, after-sales service concerns.

# Brand Direction

| Primary Color | Crimson #8B1A4A |
| --- | --- |
| Accent Color | Gold #C8A96E |
| Background | Near-black #0E0C0C |
| Display Typeface | Cormorant Garamond |
| Body Typeface | DM Sans |
| Tone | Trustworthy, premium, expert, locally rooted |

# Functional Requirements

Core Website Features

- Home, Brands (Hafele/Dorset/Labacha/Godrej/Hettich/Kich), Product Categories, About/Legacy, Contact & Map.

- Click-to-WhatsApp CTAs throughout, with section-specific pre-filled messages.

- Embedded Google Business Profile / map for the Sakchi showroom.

Explicitly Not Included

- Product checkout, cart, or payment gateway — this is a lead-generation site, not an e-commerce platform.

# Technical Requirements

| Platform / Stack | Next.js 14, Tailwind CSS |
| --- | --- |
| Hosting | Vercel |
| Domain | hardwarecollection.co (GoDaddy DNS → Vercel) |
| Build Tools | Cursor / Bolt (8 sequential vibe-coding prompts delivered) |
| Security / Performance Targets | [NEEDS INPUT — Mukesh] |

# Content Requirements

- Text/copy: Agency-authored via the 21-file knowledge base and website copy pack.

- Images: Store and product photography — to be supplied by Mukesh, art-directed by agency.

- Product data / pricing / warranty terms: [NEEDS INPUT — Mukesh].

# Deliverables

- 21-file HC-KB enterprise knowledge base (ZIP), including a droppable PROJECT_INSTRUCTIONS.md system prompt.

- Locked brand and design system.

- hardwarecollection.co domain, connected to Vercel, with live coming-soon page.

- 90-Day Sakchi Map Domination Blueprint (GMB completeness, review growth, Map Pack ranking).

- Notion Task OS — 41 tasks across 5 phases, plus Content Calendar, Response Template Library, Deliverables Vault, Review Tracker, KPI Log, and Citation Tracker.

- Website PRD and build pack (DOCX): PRD, technical spec, design system, copy, 8 vibe-coding prompts, launch checklist.

- Competitor profiles: Harsh Plywood, Sri Ram Hardware, Jalaram Hardware Stores.

- Standardized WhatsApp CTA system (919835190738) across all sections.

# Timeline & Status

| Phase | Status | Notes |
| --- | --- | --- |
| Discovery & Strategy | Complete | GMB audit, competitor intelligence, 90-Day Sakchi Map Domination Blueprint delivered |
| Knowledge Base & Systems | Complete | 21-file HC-KB delivered; Notion Task OS live (41 tasks, 5 phases, 6 databases) |
| Brand & Design System | Complete | Palette, typography, and Next.js/Tailwind/Vercel stack locked |
| Domain & Infrastructure | Complete | hardwarecollection.co purchased and connected to Vercel; coming-soon page live |
| Website Build | In Progress | PRD, technical spec, and 8 sequential vibe-coding prompts delivered; execution pending |
| Owner Inputs | Pending | GST, vendor terms, real margins, warranty policies, logo, budget, launch date — [NEEDS INPUT — Mukesh] |
| GMB / Local SEO Execution | Ongoing | Post cadence (Mon/Wed/Fri) and review generation campaign in progress |
| Launch | Pending | Original 20 May 2026 target has passed; revised date needs confirmation |

# Risks

- Naming conflict with an unrelated Kolkata-based "Hardware Collection" brand — mitigated by consistent use of "Jamshedpur," "Sakchi," or the _jsr handle suffix across all new assets.

- Original launch target (20 May 2026) has passed without a revised date — needs confirmation to avoid stalling momentum.

- Multiple knowledge base sections remain marked [NEEDS INPUT — Mukesh] (GST, vendor terms, real margins, warranty policies) — these gate certain website and CRM content from being finalized.

- No fabricated data is used anywhere in the KB or website copy; unresolved fields are placeholder-marked rather than invented.

# Acceptance Criteria

- All [NEEDS INPUT — Mukesh] fields in the knowledge base and this brief are resolved.

- Website is live at hardwarecollection.co, matches the approved PRD, and functions on mobile.

- GMB profile reaches 90%+ completeness with an active weekly post cadence.

- WhatsApp Business is fully configured with catalog, quick replies, and standardized CTAs.

- Notion Task OS is operational and being used for ongoing execution tracking.

# Sign-off

| Client Approval | Mukesh Khandelwal — Owner, Hardware Collection |
| --- | --- |
| Project Executor Approval | Aayush |
| Date | [NEEDS INPUT — Mukesh] |